## Workplan
|  | Year 1 Q4 |  |  | Year 2 Q1 |  |  | Year 2 Q2 |  |  | Year 2 Q3 |  |  | Year 2 Q4 |  |  | Year 3 Q1 |  |  | Year 3 Q2 |  |  | Year 3 Q3 |  |  | Year 3 Q4 |  |  | Year 4 Q1 |  |  | Year 4 Q2 |  |  | Year 4 Q3 |  |  | Year 4 Q4 |  |  | Year 5 Q1 |  |  | Year 5 Q2 |  |  | Year 5 Q3 |  |  | Year 5 Q4
Activity | Tasks | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
1. Existing Data Outputs
1 | PI study: Dataset prep | Nov: XXXXXXXX
1 | PI study: Analysis plan and first draft | Feb: XXXXXXXX
1 | PI study: Finalise analysis | May: XXXXXXXX
1 | PI study: Manuscript draft | Aug: XXXXXXXXXX
1 | Ghanaian study: Dataset prep | Nov: XXXXXXXX
1 | Ghanaian study: Analysis plan and first draft | Feb: XXXXXXXX
1 | Ghanaian study: Finalise analysis | May: XXXXXXXX
1 | Ghanaian study: Manuscript draft | Aug: XXXXXXXXXXXX
1 | Calabar Nigerian study: Dataset prep | Feb: xxxxxxxx
1 | Calabar Nigerian study: Analysis plan and first draft | Dec: xxxxxxxxxx
1 | Calabar Nigerian study: Finalise analysis | Feb: xxxxxxxx
1 | Calabar Nigerian study: Manuscript draft | May: xxxxxxxx
1 | Sierra Leone study 1: Dataset prep | Feb: xxxxxxxx
1 | Sierra Leone study 1: Analysis plan and draft | Aug: xxxxxxxx
1 | Sierra Leone study 1: Finalise analysis | Nov: xxxxx
1 | Sierra Leone study 1: Manuscript draft | Dec: xxxxxxxxxx
1 | Sierra Leone study 2: Dataset prep | Feb: xxxxxxxx
1 | Sierra Leone study 2: Analysis Plan and draft | Aug: xxx; Sep: xxxxx
1 | Sierra Leone study 2: Finalise Analysis | Nov: xxxxxx
1 | Sierra Leone study 2: Manuscript draft | Dec: xx; Jan: xxxxxxx
xx
| Stakeholders workshop 1 | Dec: xxxxxxx; Jul: xxxxx; Oct: x; Mar: xxxxxxxx
xxxxx
6 | Stakeholders workshop 2
6 6 | Stakeholders workshop 3
6 | Dissemination of Key Findings | Aug: xxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxx
6 | Policy Brief 1 | Jan: xxxxxxx
6 | Policy Brief 2 | Jan: xxxxxxx
6 | Policy Brief 3 | Aug: xxxxxxxx; May: xxxxxxxxxx
6 | Policy Brief 4
6 | Policy Brief 5
7. Reporting
7 | Progress Reporting | Apr: xxx; Jul: xx; Oct: xx; Jan: xx; Apr: xx; Jul: xx; Oct: xx; Jan: xx; Apr: xx; Jul: xx; Oct: xx; Jan: xx; Apr: xx; Jul: xx; Oct: xx; Jan: xx
7 | Annual Reporting | Dec: xxxx; Dec: xxxxx; Dec: xxxxx; Dec: xxxxx
7 | Report Review | Dec: xxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxx